## UK ADSF Grant Reporting
UK Airspace Design Support Fund Reporting Requirement*
*PLEASE CHECK WORDING OF THE GRANT FUNDING AGREEMENT FOR DETAIL
Progress Reporting
Please populate all tabs
This form should be completed in accordance with the guidance in Chapter 3 of CAP 3231: UK Airspace Design Support Fund Application Process and Guidance available at:
www.caa.co.uk/cap3231
Completed reports should be submitted to the CAA at the following address:
airspace.modernisation@caa.co.uk
Support Fund Reference No:
Report compiled by:
On behalf of:
Reporting period:

## SoW Progress
Statement of Work Progress Report
SoW Item (line number and deliverable / task) | Planned Date(s) | Actual / Adjusted Date(s) | Completion Status | Progress Update in Reporting Period | Not started
1 - Consultation response analysis & CRD production | 06/05/2026 - 03/06/2026 | 06/05/2026 - 28/06/2026 | Not started | Delay due to receiving 500 responses more than anticipated. Draft CRD due delivery 22 Jun, final 28 Jun | Completed
10%
20%
30%
40%
50%
60%
70%
80%
90%

## Cost Report
Cost Report
SoW Line | Funded Activity / Deliverable | Claimed Costs | Actual Costs | Variance |  | Reason for Variance
1 | Consultation response analysis & CRD production | 55000 | 57000 | 2000 | 3.636% | Overspend of £2,000 on contractor cost (+5 days @£400 PD) due to receiving 800 more consultation responses than anticipated
2 |  |  |  | 0
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
| Total | 55000 | 57000 | 2000 | 3.636%

## Delivery Schedule
Delivery Schedule
| Work package | Deliverables / Key Milestones | Due | Progress % Complete | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11
[5 empty] | Planned Activity Duration |  |  | Delay
Progress To Date
ACP Stage X Gateway

## Risk Register
Risk Register
Risk ID | Risk Description | Impact pre-mitigation | Mitigation | RAG
1 |  |  |  | Green | Medium | Amber
2 |  |  |  | Amber | Low | Red
3 |  |  |  | Red
4
5
6
7
8
9
10